## Milestones
Dealine Date | Milestone | Objective | Deliverables | Tasks | Assignee | Status | Estimation | Actual Duration
19.10.2015 | MS1 |  | RSD v1.0 |  | All Team | Finished
26.10.2015 | MS2 |  | RSD v1.1 + Mockups |  | All Team | Finished
02.11.2015 | MS3 |  | DSD v1.0 + Detailed Project Plan for MS3 + First Code Commit | Create project plan in Google Sheets | Alper | Finished
|  |  |  | Write detailed tasks for milestone MS3 in project plan | Alper | Finished
|  |  |  | Create Github Issues and Assign them | All Team | In Progress
|  |  |  | Decide technical infrastructure of the application | All Team | In Progress
|  |  |  | Create DSDv1.0 Template in Google Docs | Alper | Finished
|  |  |  | Write DSDv1.0 - Section 1 | Alper | Finished
|  |  |  | Write DSDv1.0 - Section 2 | Hasancan | In Progress
|  |  |  | Write DSDv1.0 - Section 2.1 | serkan | Finished
|  |  |  | Write DSDv1.0 - Section 2.2 | Emre Demirel | In Progress
|  |  |  | Write DSDv1.0 - Section 2.3 | serkan | Finished
|  |  |  | Write DSDv1.0 - Section 3 | Hasancan | In Progress
|  |  |  | Write DSDv1.0 - Section 3.1 | Serkan | Finished
|  |  |  | Write DSDv1.0 - Section 3.2 | Alper | Finished
|  |  |  | Write DSDv1.0 - Section 3.3 | Hasancan | In Progress
|  |  |  | Write DSDv1.0 - Section 4 | Emre Gürer | Finished
|  |  |  | Write DSDv1.0 - Section 5 | All Team | In Progress
|  |  |  | Generate application code base and commit to github | Alper | Finished
09.11.2015 | MS4 | Finalizing the design specification document | DSD v1.1
23.11.2015 | MS5 | Preparing for the first demo with the features in deliverables column | Welcome Page
Registration Page
Login Functionality
User Profile Page
User Main Page
Community Creation Page
Community Detail Page
Create Post Function
07.12.2015 | MS6 | Preparing for the second demo with the features in deliverables column | Community Join Requests Page
Upload Resources Page
Community Resource List Page
Schedule Meeting Page
Meeting Information Page
Community Meeting List
21.12.2015 | MS7 | Preparing for the second demo with the features in deliverables column | Live Meeting Page
Create MOM Function
04.01.2016 | MS8 | Deploying the application into server and creating the software product manual | Deployment + SPM v1.0